## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US 01 | As a visitor,I should be able to "Register" to the application as a seller by providing my credentials, so that I will be able to access account. | Must Have | 5 | Adhishree-1149663 | 3- Completed
|  | US 01 | As a visitor,I should be able to "Register" to the application as a buyer by providing my credentials, so that I will be able to access account. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 02 | As a privileged buyer, I want to manage products and cart page, so that I can buy specific products.(login) | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 02 | As a seller, I want to manage products and orders, So that I should be able to update status of orders.(login) | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 17 | Deactivate Buyer and Seller Account | Must Have | 10 | Adhishree-1149663 | completed
1 | 1 | US 03 | Get buyer details. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 03 | Get seller details. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 04 | Get buyer details with specific buyerId. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US04 | Get seller details with specific sellerId. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 05 | As a buyer, I want to have product in my wishlist. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 05 | As a buyer, I want to save my product in cart. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 06 | delete product from Wishlist. | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 06 | delete product from cart | Must Have | 5 | Adhishree-1149663 | completed
1 | 1 | US 07 | Add products. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 08 | Get product details. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 08 | Get product details from productId | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 08 | Get product details from product name. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 08 | Get product details from product category. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 09 | Update stock of products. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 10 | Get all subscribed products. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 10 | Get subscribed products with buyer Id. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 11 | Delete product using product ID. | Must Have | 5 | Harshvardhan-1150130 | completed
1 | 1 | US 12 | Get all orders. | Must Have | 5 | Aishwarya-1149568 | completed
1 | 1 | US 12 | Get orders using order ID. | Must Have | 5 | Aishwarya-1149568 | completed
1 | 1 | US 13 | place order details. | Must Have | 5 | Aishwarya-1149568 | completed
1 | 1 | US 13 | Re-order details. | Must Have | 5 | Aishwarya-1149568 | completed
1 | 1 | US 14 | Get products order by product ID. | Must Have | 5 | Aishwarya-1149568 | completed
1 | 1 | US 15 | Delete order. | Must have | 5 | Aishwarya-1149568 | completed
1 | 1 | US16 | Update Order Status | Must Have | 5 | Adhishree-1149663 | completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on F2: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 99 | 10 | 8 | 2
SPRINT 1 BACKLOG
US-01 | T1 | create DTO entity of buyer and seller | 2021-09-01 | 2021-09-01 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | create validator class of buyer and seller | 2021-09-02 | 2021-09-02 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T3 | create service class function for seller and buyer registration | 2021-09-03 | 2021-09-05 | Adhishree-1149663 | Coding | 3- Completed | 10 | 5 | 4 | 1
| T4 | create controller class function buyer and seller registration | 2021-09-06 | 2021-09-06 | Adhishree-1149663 | Coding | 3- Completed | 4 | 0 | 0 | 0
| T5 | create DTO entity of cart and wishlist | 2021-09-01 | 2021-09-01 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-02 | T1 | create login method implementation of buyer and seller | 2021-09-03 | 2021-09-03 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T1 | Validate Credentials for buyer login | 2021-09-03 | 2021-09-03 | Adhisree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | Validate Credentials for seller login | 2021-09-03 | 2021-09-03 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-03 | T1 | create get buyerdetails and seller details | 2021-09-03 | 2021-09-03 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-04 | T1 | create get buyerdetails and seller details with buyerid sellerid | 2021-09-03 | 2021-09-03 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-05 | T1 | created wishlist method | 2021-09-04 | 2021-09-04 | Adhishree-1149663 | Coding | 3- Completed | 5 | 0 | 0 | 0
| T2 | created cart method | 2021-09-05 | 2021-09-05 | Adhishree-1149663 | Coding | 3- Completed | 5 | 0 | 0 | 0
US-06 | T1 | created delete whishlist and cart method implementation | 2021-09-05 | 2021-09-05 | Adhishree-1149663 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-17 | T1 | Created function for deactivae Buyer Account | 2021-09-05 | 2021-09-05 | Adhishree-1149663 | Coding | 3-Completed | 2 | 0 | 0 | 0
| T2 | Created function for deactivae Seller Account | 2021-09-05 | 2021-09-05 | Adhishree-1149663 | Coding | 3-Completed | 2 | 0 | 0 | 0
US-07 | T1 | create DTO entity of product | 2021-09-01 | 2021-09-01 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | create validator class of product | 2021-09-02 | 2021-09-02 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T3 | create service class function of product | 2021-09-03 | 2021-09-05 | Harshavardhan-1150130 | Coding | 3- Completed | 10 | 5 | 4 | 1
| T4 | create controller class function product | 2021-09-06 | 2021-09-06 | Harshavardhan-1150130 | Coding | 3- Completed | 4 | 0 | 0 | 0
| T5 | created add product | 2021-09-03 | 2021-09-03 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-08 | T1 | created Get product details. | 2021-09-04 | 2021-09-04 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | created Get product details from product ID. | 2021-09-04 | 2021-09-04 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T3 | created Get product details from product name. | 2021-09-04 | 2021-09-04 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T4 | created Get product details from product category. | 2021-09-04 | 2021-09-04 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-09 | T1 | Created update stock method implementaion | 2021-09-04 | 2021-09-04 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-10 | T1 | created Get all suscribed products. | 2021-09-05 | 2021-09-05 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | created Get suscribed products with buyer Id. | 2021-09-05 | 2021-09-05 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-11 | T1 | created Delete product using product ID. | 2021-09-06 | 2021-09-06 | Harshavardhan-1150130 | Coding | 3- Completed | 2 | 0 | 0 | 0
US 12 | T1 | created Get all orders. | 2021-09-03 | 2021-09-03 | Aishwarya-1149568 | Coding | 3- Completed | 2 | 0 | 0 | 0
| T2 | created Get orders using order ID. | 2021-09-03 | 2021-09-03 | Aishwarya-1149568 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-13 | T1 | created place order details. | 2021-09-04 | 2021-09-04 | Aishwarya-1149568 | Coding | 3- Completed | 3 | 0 | 0 | 0
| T2 | created Re-order details. | 2021-09-04 | 2021-09-04 | Aishwarya-1149568 | Coding | 3- Completed | 4 | 0 | 0 | 0
US-14 | T1 | craeted Get products order by product ID. | 2021-09-05 | 2021-09-05 | Aishwarya-1149568 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-15 | T1 | craeted Delete order. | 2021-09-06 | 2021-09-06 | Aishwarya-1149568 | Coding | 3- Completed | 2 | 0 | 0 | 0
US-16 | T1 | Created Update Order Status | 2021-09-06 | 2021-09-06 | Adhishree-1149663 | Coding | Completed | 2 | 0 | 0 | 0
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Sprint II Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3
[8 empty] | 11 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | T1 | Project Configuration | 2021-09-10 | 2021-09-11 | Adhishree-1149663,Harshavardhan-1150130-, Aishwarya-1149568 | Build | 3- Completed | 4 | 0 | 0 | 0
| T2 | Minor Enhancement | 2021-09-11 | 2021-09-11 | Adhishree-1149663,Harshavardhan-1150130, Aishwarya-1149568 | General | 3- Completed | 2 | 0 | 0 | 0
US-02 | T1 | Project Configuration | 2021-09-10 | 2021-09-11 | Adhishree-1149663,Harshavardhan-1150130, Aishwarya-1149568 | Integration | 3- Completed | 3 | 0 | 0 | 0
| T2 | Minor Enhancement | 2021-09-11 | 2021-09-11 | Adhishree-1149663,Harshavardhan-1150130, Aishwarya-1149568 | General | 3- Completed | 2 | 0 | 0 | 0
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work

## Retrospection
Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint1-01 sep 2021 | Sprint1-06 sep 2021 | Adhishree-1149663,Harshavardhan1150130,Aishwarya-1149568 |  |  |  | completed
Sprint2-07 sep 2021 | Sprint2-12 sep 2021 | Adhishree-1149663,Harshavardhan-1150130,Aishwarya-1149568 |  |  |  | completed

## Product Backlog Grooming
Sprint | US ID | Points Discussed
sprint1 | US-01 | registration
sprint1 | US-02 | login
sprint1 | us-03 | get buyer and seller details
sprint2 |  | sonarcloud
sprint2 |  | aws

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken
sprint1 | US-01 | 2021-09-01 | Adhishree-1149663 | User Details |  | completed
sprint1 | US-07 | 2021-09-02 | Harshavardhan-1150130 | product details |  | completed
sprint1 | US-12 | 2021-09-03 | Aishwarya-1149568 | Order details |  | completed
sprint2 |  | 2021-09-07 | Adhishree-1149663,Harshavardhan-1150130, Aishwarya-1149568 | sonar cloud |  | completed
sprint2 |  | 2021-09-10 | Adhishree-1149663,Harshavardhan-1150130, Aishwarya-1149568 | Aws |  | completed